## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## Content
Election Machine
Scrum Doc, Software Dev Project Spring 2022
Team2: Basil Omsha, Adewale Salami
Content
1) Product backlog
2) Tasks
3) Sprint planning meeting
3) Sprint Backlog -1
4) Sprint Backlog -2

## ProductBacklog
Product Backlog - Project Title
User Stroy | Story Point(s) | Priority
As an admin, I am able to log in. | 6 | 1
As an dmin, I am able to add, edit and remove registered candidates. | 6 | 1
As an admin, I am able to add, edit and remove (users and registered candidates) questions. | 6 | 1
As a citezens, I am able to register as voter. | 4 | 1
As a nominee, I am able to register and become a registerd candidate. | 4 | 1
As a registered candidate, I am able to answer questions, and are able to edit and delete my answer/s. | 6 | 3
As a registered candidate, I am able to see a list of other registered candidates and their answers. | 2 | 3
As a voter, I am able to answer questions. | 4 | 1
As a voter, I am able to see all registered candidates. | 2 | 3
As a voter, I am able to filter registered candidates based on my own answers. | 8 | 3
As a voter, I am able to see registered candidates answered questions. | 2 | 5
As a voter I am able to read about each candidate campaign and their goals. | 2 | 5
Priorities
1= Vital
3= important
5= The least important
2
6
10
4
8
Walk in a park
Veteran
Challenging
Medium
Hard
Story Points

## Tasks
User stories and their related tasks
User Stories | Tasks
Create a login page
Create a table for admins in the DB with encrypted password features in the DB
As an admin, I am able to log in. | The login page esablishes a connection with the db and checks if the credentials are available in the db
If the username or password are wrong, inform the user with an error message
Design an admin page UI
As an dmin, I am able to add, edit and remove registered candidates. | Connects to registered candidates db
Able to edit, select, inseret and drop the db info
Connects also to users db
As an admin, I am able to add, edit and remove (users and registered candidates) questions. | Able to edit, select, inseret, and drop the db info
Create the front page where users can select whether they want to register as voters or candidates with a link for admins login page.
As a citezens, I am able to register as voter. | Create a registration form for voters that sends info to the voters db
Create registration form for candidates that connects to candidates db
As a nominee, I am able to register and become a registerd candidate.
Create a candidate page
As a registered candidate, I am able to answer questions, and are able to edit and delete my answer/s. | Questioned answered are updated to the candidates db
Able to edit, inseret or drop the questions from the candidates db
Add a candidates list to the candidate page
As a registered candidate, I am able to see a list of other registered candidates and their answers. | Show the answers each candidate answered
Create a voter page
As a voter, I am able to answer questions. | Questioned answered are updated to the voters db
Create a list of candidates in the voter page
As a voter, I am able to see all registered candidates.
Connect voters db with candidates db
As a voter, I am able to filter registered candidates based on my own answers. | Create a script that looks for matching key words in the answers saved in the databases
Add a read more bottun to the candidates list to see their answered questions
As a voter, I am able to see registered candidates answered questions.
The read more button links to the page where voters can see all the info about candidates and their answered questions
As a voter I am able to read about each candidate campaign and their goals.

## sprint_planning_meetings
Spring Planning | Participants
Sprint 1 Week 13 | Adewale | Basil | -
Location | Online | Online |  | If physically present mark X
Date: 28.3.2022
Sprint 2 Week 14
Online
4.4.2022 - 10.4.2022
Sprint 3 Week 15
Location
Date
Sprint 4 Week 16
Location
Date
Sprint 5 Week 17
Location
Date
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## sprint_backlog_sprint1
Sprint Backlog : Sprint 1 28.3.2022 - 03.4.2022
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Create GitHub repository |  | All
Make sure we all have the same MySQL version |  | All
Make sure our environment works properly |  | All
User Story: As a citezens, I am able to register as voter. | 4 | Basel
Create HTML front page, creat links to voters and nominees registiration pages | Done
Create HTML voters registeration page. | Done
Create Election machine DB with the necessarry tables. | In progress
Connect voter registration form to database table | Done
User Story: As a nominee, I am able to register and become a registerd candidate. | 4 | Basel
Create HTML nomniees registeration page.
User Story: As an admin, I am able to log in. | 6 | Basel
Create a login page
Create a table for admins in the DB with encrypted password features in the DB (salt)
The login page esablishes a connection with the db and checks if the credentials are available in the db
If the username or password are wrong, inform the user with an error message
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0

## sprint_backlog_sprint2
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task : Make a list of categories of products | 2 | Pekka | Ongoing | 2 | 3 | 4 | 4 | 4
Task : List products based on categories | 2 | Juha |  | 2 | 1 | 7 | 3 | 1
Task : Search products | 4 | Johanna |  | 2 | 2 | 6 | 2 | 4
Task: Display products | 2 | Markku |  | 2 | 4 | 5 | 5 | 6
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 8 | 10 | 22 | 14 | 15